## Instructions
DMAIC
Define
Measure
Analyze
Improve
Control
@2019 SSGI. For Personal Use Only. Other Uses Require Written Permission.
DMAIC is a powerful tool in the Lean Six Sigma toolkit because it represents a framework within which Lean SIx Sigma projects unfold. It defines the five major steps followed by any project and guides a team through these stages to ensure a logical and thorough approach to studying, evaluating and improving process flow. Complete the template found on the following sheet by entering the information suggested below.
Identify the target process. Specify the exact nature of the problem. Describe the problem in writing. Summarize the Voice of the Customer. Determine those dimensions of the problem that are Critical to Quality. Clarify the boundaries; what will be considered and what will not be considered as part of the project.
Define the data that best represents system inputs, outputs and process parameters. Collect data to establish the performance of the current state. Establish the gap between the current state of the process and the desired or proposed state of the process. Assess the measurement system to assure that the data collected best represents the nature of the problem.
Explore the causes of the problem. Find its root cause. Consider how inputs affect outputs. Will the inputs you have isolated as the root cause reliably affect outcomes? Identify the tools such as SIPOC diagrams, process flow charts, X-Y matrices, Multi-Vari charts and FMEA that could be helpful in addressing the analysis phase.
Identify as many solutions as possible. Engage in brainstorming sessions. Choose the solution that is easiest to implement and one that is more likely to be accepted by those responsible for the operational process. Create an implementation plan.
Create a control plan that identifies where in the process control points will be introduced. Choose the correct control chart. Design these charts. Document the control plan.

## Template
DMAIC
The following reminders should help you fill out the template:
Define
Identify the target process.
Describe the Problem.
Summarize the Voice of the Customer.
Identify Critical to Quality
Clarify Boundaries.
Measure
Identify the inputs and outputs
How can they be measured?
Identify process parameters?
How can they be measured?
Estimate the gap between the old and new
Validate measurment methods
Analyze
Identify possible causes.
Find root cause.
How do inputs affect outputs?
Identify the tools that will be used.
Improve
Identify as many solutions as possible.
Choose best and simplest solution.
Create an implementation plan.
Control
Where will control points be introduced?
Create control plan.
Design control charts.
Document plan.
@2019 SSGI. For Personal Use Only. Other Uses Require Written Permission.
The target is the call answering process. The problem is that customers have been experiencing increasing hold times before their calls are answered. The Voice of the Customer expects prompt service and complete answer to questions. Both promptness and quality of answers represent the Critical to Quality dimensions of the project. The boundaries of the project include faster response times, and better answers, but they do not necessarily include a review of the methods and procedures for processing the paperwork required for insurance approval or claim submission. Improving that process can be left to another project.
The inputs to the process include staff training, competitive salaries paid in the industry, website completeness, and the design of the process. The primary issue in this project has been identified as the time it takes to respond to a customer at the call center and the time it takes to process their calls. Holding time can be measured in minutes. They can be measured by sampling a set of calls. The gap between the old and new system compares the time it took to respond under the existing system and the expected time for the new system.
One cause for the current problem may be that the representatives are asked questions for which they have inadequate knowledge. Representatives are expected to answer questions about general information, help preparing forms, payment information, how to file a claim and more. If the process is redesigned, and specialists used, then customer satisfaction, the output of this process, should benefit. The tools used will include X-Y matrix, Value Stream maps, Regression, Multi-Vari charts, Hypothesis testing, and control charts.
The results of the analysis phase will be used to guide the design of a trial system. The system will be monitored, and the results tested to determine if, in fact, the new system is better than the old. If appropriate, the new system will be implemented at both facilities.
To assure that the process, once implemented, will continue to perform as expected, control charts for means and variances will be designed. These charts will focus on one or more of the following: hold times for incoming calls; processing time for screening; hold time before a specialist answers the call; processing time for specialists; and customer satisfaction. Finally, the system will be documented for future reference.